## Slide 1: National Geospatial Information Management Strategy Action Plan Update 29 January, 2020
M. Hicks
Lands Department
January 29, 2020

## Slide 2: Five Strategic Goal
Governance  6 action points
Data  4 action points
Access  4 action points
Interoperability  4 action points
Development  4 action points

## Slide 3
1. Governance | 
Action | Status
1. To review the role and composition of the Fiji Geospatial Council (previously known as the Fiji Land Information Council) to ensure a full range of interests of the Fiji geospatial industry is represented. | Completed
2. To review any existing legislation and regulation relating to the geospatial industry, and recommend changes where appropriate | Pending
3. Coordinate the implementation of the National Geospatial Strategy. | In Progress
Notes: Action 1: Approved by Cabinet in 2018
Action 2: SGs (Refer to document)
Action 3: Coordinated by the FGTAC

## Slide 4
1. Governance | 
Action | Status
4. Monitor the progress of each of the strategic goals of the Strategy. | In Progress
5. Carry out an education and awareness programme to inform the geospatial industry and the wider public about the value and benefits of geospatial information. | Website User Group Newsletter
6. Provide a mechanism for coordinating resources between different sectors of the industry to facilitate joint data acquisition programmes. | In Progress
Notes: Action 5: Monitored by the FGTAC
Action 6: User Group have monthly meetings to discuss GIS issues, Lands through the VanuaGIS awarenes also promotes the benefits of using geospatial information

## Slide 5
2. Data | 
Action | Status
1. Determine a list and description of the fundamental datasets that are critical to the development of a robust and efficient geospatial industry | Completed Cabinet Paper
2. Identify the custodian of each of these fundamental datasets and put in place a data custodian system that ensures the integrity of the fundamental data. | In Progress Upload to Website
Notes: Action 1: Proposal to submit a cabinet paper on the adopted fundamental themes and it data sets
Action 2: Custodians have been identified. Match the data sets in the list provided to the fundamental data themes.

## Slide 6
2. Data | 
Action | Status
3. Evaluate the quality of each fundamental dataset and develop a process for improving the quality of fundamental data where necessary. | Pending
4. Ensure that the fundamental datasets meet the needs of the nation. | Pending
Notes: Action 3: FGTAC needs to meet and discuss this as it can get very technical
Action 4: Not only meets the national needs, but aligns to the meeting of the SDGs

## Slide 7
3. Access | 
Action | Status
1.Develop metadata, to an international standard, for all fundamental datasets. | Completed Awareness
2. Publish metadata and processes for accessing the fundamental datasets in a manner that is open and accessible. | Completed Upload to Website
Notes: Action 1: Through User Group meetings
Action 2: Submission to Cabinet

## Slide 8
3. Access | 
Action | Status
3. Encourage public agencies and non-government organisations to make their non-fundamental datasets available following agreed practices and procedures. | Pending Data Sharing Policy
4. Develop and encourage access to the fundamental data and provide a framework for adding value to the fundamental data. | Pending
Notes: Action 3: FGTAC to develop a data
Action 4: This will be developed once the data sharing policy is established

## Slide 9
4. Interoperability | 
Action | Status
1. Promote the concept of interoperability among the fundamental data custodians. | Pending
2. Support the development of the necessary technical standards and procedures to implement interoperability of fundamental datasets. | Completed
Notes: Action 1: Most geospatial experts are aware that of the compatibility of format between softwares’ and know to interchange data format using various techniques.
Action 2: This is embedded in the documentation for the fundamental data themes

## Slide 10
4. Interoperability | 
Action | Status
3. Encourage non-fundamental data custodians to implement interoperability. | Software data formats are interoperable
4. Support the development of a national geospatial network where all fundamental data is available, and on which non-fundamental data can be made available. | VanuaGIS and the Lands hub
Notes: Action 3:The main issue is what standard that is used by agencies that capture information and if there are quality controls in place to ensure that data collected be fundamental or non fundamental is accurate and relevant.
Action 4: Displayed on the VanuaGIS portal

## Slide 11
5. Development | 
Action | Status
1. Undertake a human and technical capacity inventory to identify gaps and overlaps of capacity | Pending
2. Encourage the establishment and development of dedicated higher education training opportunities in geospatial science and technology in Fiji. | In Place
Notes: Action 1: Unfortunately this has not moved, as we have been focusing on establishing the fundamental themes along with the data sets.
Action 2: Our local universities have programs in place that cater for geospatial information management programmes with an emphasis in areas such as surveying, GIS, land management, remote sensing and programming.

## Slide 12
5. Development | 
Action | Status
3. Encourage and facilitate access to shared training and technical resources. | In Place
4. Establish an annual national geospatial conference to promote information sharing and network at all levels of the industry. | Funding and organising issue
Notes: Action 3: Done through our collaboration for training such use of drones and the processing of imagery and working with other agencies such Ministry of employment to help with their GIS efforts.
Action 4: Previous Conference, however there have been funding and organising issues.

## Slide 13
Vinaka